## Slide 1: MEDIUM VOLTAGE SUPPLY CONNECTION IN ENERGYSENSE (MVSC)
WEEKLY PROJECT STATUS
18th April 2024

## Slide 2
KEY MILESTONES | PLANNED START | PLANNED END | ACTUAL START | ACTUAL END | STATUS
User Requirement Specification (URS) & Joint Application Design (JAD) Session | 25-Feb-23 | 3-Mar-23 | 25-Feb-22 | 21-Jul-22 | C
User Requirement Sign-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 |  | C
System Design Session | 4-Mar-23 | 7-Mar-23 | 2-Jan-23 | 4-Mar-23 | C
Development |  |  |  |  | 
Integration with myTNB | 26-Aug-23 | 7-Aug-23 |  |  | c
Maintain Old Application | 8-Aug-23 | 10-Aug-23 |  |  | 
Application Number | 11-Aug-23 | 15-Aug-23 |  |  | 90%
Application Status | 16-Aug-23 | 18-Aug-23 | 31-Jul-23 |  | 90%
Application Stages Timeline | 21-Aug-23 | 31-Aug-23 | 31-Jul-23 |  | 90%
Getting Electricity (GE) Eligibility | 1-Sept-23 | 8-Sept-23 |  |  | 90%
Application Submission (non-draft) | 22-Sept-23 | 29-Sept-23 |  |  | 90%
UPCOMING 2 WEEKS ACTIVITIES
Nashmi to share latest FS/FD Document to Nurel Internal Pre – SIT Test Ticket number from Ikram Lim on AWS issue Nurel to create the letter to work at TNB premise
TRAINING & CLOSE
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY
PROJECT PROGRESS | Planned Start
Actual % | Planned %
Chart: 
BUILD
ANALYSE & DESIGN
PLANNING
INITIATION
TRAINING & CLOSE
ACHIEVEMENTS/ KEY HIGHLIGHTS
Completed on time
On track
On going but might be delayed
Completed but delay
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 18th April 2024 | CONTRACT PERIOD: | 3 years
ONGOING ACTIVITIES
Application Status Application Stages Timeline Application Number Getting Electricity (GE) Eligibility Application Submission (non-draft) Usability Test Sign-off Code merge between MVSC and myTNB. Bug Fixing
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 14.8 | 85.2
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 2.7 | 97.3

## Slide 3
KEY MILESTONES | PLANNED START | PLANNED END | ACTUAL START | ACTUAL END | STATUS
BCRM SR Number | 2-Oct-23 | 9-Oct-23 |  |  | 90%
ICPP Work Order Number | 26-Jul-23 | 28-Jul-23 |  |  | c
Basic Information | 31-Jul-23 | 2-Aug-23 | 31-Jul-23 |  | c
Notification Email Recipient | 3-Aug-23 | 7-Aug-23 | 8-Aug-23 |  | c
Technical Document - Normal Documents | 26-Jul-23 | 15-Aug-23 | 26-July-23 |  | 93%
Technical Document - Other Documents | 16-Aug-23 | 31-Aug-23 | 26-July-23 |  | 90%
Technical Document - Map A Digital Form | 1-Sept-23 | 26-Sept-23 | 26-July-23 |  | 92%
Technical Document – Others | 27-Sept-23 | 12-Oct-23 |  |  | 90%
Technical Review | 8-Aug-23 | 23-Aug-23 | 8-Aug-23 |  | 95%
Ulasan Teknikal | 24-Aug-23 | 31-Aug-23 | 26-July-23 |  | 90%
Getting Electricity (GE) Qualification | 1-Sept-23 | 5-Sept-23 |  |  | 90%
Update Business Area | 6-Sept-23 | 13-Sept-23 |  |  | 90%
Submit Site Progress | 26-Jul-23 | 7-Aug-23 | 26-July-23 |  | c
Supply Required Date | 8-Aug-23 | 5-Sept-23 | 12-Sept-23 |  | c
Appointment | 6-Sept-23 | 20-Oct23 | 21-Sept-23 |  | 95%
Connection Charges | 14-Sept-23 | 12-Oct-23 |  |  | c
UPCOMING 2 WEEKS ACTIVITIES
Nashmi to share latest FS/FD Document to Nurel Internal Pre – SIT Test Ticket number from Ikram Lim on AWS issue Nurel to create the letter to work at TNB premise
TRAINING & CLOSE
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY
PROJECT PROGRESS | Planned Start
Actual % | Planned %
Chart: 
BUILD
ANALYSE & DESIGN
PLANNING
INITIATION
TRAINING & CLOSE
ACHIEVEMENTS/ KEY HIGHLIGHTS
ICPP Work Order Number Basic Information Notification Email Recipient
Completed on time
On track
On going but might be delayed
Completed but delay
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 18th April 2024 | CONTRACT PERIOD: | 3 years
ONGOING ACTIVITIES
Assigning requirement/task for developer. BCRM SR Number Basic Information Technical Document - Normal Documents Ulasan Teknikal Code merge between MVSC and myTNB. Bug Fixing
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 14.8 | 85.2
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 2.9 | 98.1

## Slide 4
KEY MILESTONES | PLANNED START | PLANNED END | ACTUAL START | ACTUAL END | STATUS
Technically Complete | 26-Jul-23 | 2-Aug-23 |  |  | 
myTNB Dynatrace integration | 3-Aug-23 | 15-Aug-23 |  |  | 
EnergySense | 16-Aug-23 | 5-Spt-23 | 8-Aug-23 |  | C
Overall | 6-Sept-23 | 12-Oct-23 |  |  | 
Usability Testing for myTNB Portal | 23-Oct-23 | 16-May-24 | 8-Aug-23 |  | 80%
Code merge between MVSC and myTNB. | 3-Nov-23 | 9-Nov-24 |  |  | C
System Integration Test (SIT) MVSC with ICPP | 25.-Mar-24 | 26-April-24 | 25-Mar-24 |  | 80%
Final System Integration Test (SIT) | 29-Apr-24 | 24-May-24 |  |  | 
Final User Acceptance Test (UAT) | 27-May-25 | 14-June-24 |  |  | 
Deployment to Production Environment & Go Live | 17-June-24 | 26-June-24 |  |  | 
UPCOMING 2 WEEKS ACTIVITIES
Nashmi to share latest FS/FD Document to Nurel Internal Pre – SIT Test Ticket number from Ikram Lim on AWS issue Nurel to create the letter to work at TNB premise
TRAINING & CLOSE
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY
PROJECT PROGRESS | Planned Start
Actual % | Planned %
BUILD
ANALYSE & DESIGN
PLANNING
INITIATION
TRAINING & CLOSE
ACHIEVEMENTS/ KEY HIGHLIGHTS
Energy Sense Code merge between MVSC and myTNB.
Completed on time
On track
On going but might be delayed
Completed but delay6
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 18th April 2024 | CONTRACT PERIOD: | 3 years
ONGOING ACTIVITIES
Usability Testing for myTNB Portal System Integration Test (SIT) MVSC with ICPP
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 14.8 | 85.2
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 2.9 | 98.1

## Slide 5
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 28th July 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 18th April 2024 | CONTRACT PERIOD: | 3 years
TOP 3 ISSUES AND RECOMMENDATIONS | PLANNED START |  |  |  | ACTUAL START | 
No. | Issue | Category | Resolution | PIC | Due Date | Status
1 | VPN cannot be accessed | High | Developers to go to TNB premise to continue working on development | Innotech / TNB | - | Open
TOP 3 RISKS AND MITIGATIONS | PLANNED END |  |  |  |  | ACTUAL START |  | 
No. | Risk | Likelihood | Impact | Category | Mitigation | PIC | Due Date | Status
ACTION LIST | PLANNED START |  | ACTUAL START | 
No. | Action | PIC | Due Date | Status
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY

## Slide 6
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 28th July 2023
PROJECT MANAGER (Innotech): | Nashmi Shah Nalkatli | REPORT DATE: | 18th April 2024 | CONTRACT PERIOD: | 3 years
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY

## Slide 7
PAYMENT MILESTONES | PAYMENT MILESTONES |  | 
No. | Milestones Description | % | Status
MVSC IMPLEMENTATION |  |  | 
1. | Kick-Off and URS Sign-Off | 30% | PAID
2. | Sprint 1 UAT Sign Off and Tech Service Go Live | 20% | 
3. | Sprint 2 UAT Sign Off and Tech Service Go Live | 20% | 
4. | Sprint 3 UAT Sign Off and Tech Service Go Live | 20% | 
5. | Technical Documentation and Service Proj Closure | 10% | 
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 28th July 2023
PROJECT MANAGER (Innotech): | Nashmi Shah Nalkatli | REPORT DATE: | 27th July 2023 | CONTRACT PERIOD: | 3 years
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY