## Timeline 10 October 2023 (3)
Medium Voltage Supply Connection - MVSC Project Timeline |  | Target Start Date | Target Comp. Date | Actual Start Date | Actual End Date | STATUS
No | Activities
1 | User Requirement Specification (URS) & Joint Application Design (JAD) Session | Tue 25/2/23 | Mon 3/3/23
| User Requirement Specification (URS) | Tue 25/2/23 | Wed 26/2/23 | Tue 25/2/23 | Wed 26/2/23 | C
| - EnergySense MVSC Core functions | Thu 27/2/23 | Fri 28/3/23 | Thu 27/2/23 | Fri 28/3/23 | C
| SOA (MVSC-ICPP) interfaces | Mon 3/3/23 | Mon 3/3/23 | Mon 3/3/23 | Mon 3/3/23 | C
2 | System Design Session | Tue 4/3/23 | Fri 7/3/23
| - System Design for Database | Tue 4/3/23 | Thu 5/3/23 | Tue 4/3/23 | Thu 5/3/23 | C
| - System Design for User Interface | Wed 5/3/23 | Thu 6/3/23 | Wed 5/3/23 | Thu 6/3/23 | C
| - System Design for Functional Workflow | Thu 6/3/23 | Fri 7/3/23 | Thu 6/3/23 | Fri 7/3/23 | C
| User Requirement Sign-off | Fri 7/3/23 | Fri 7/3/23 | Fri 7/3/23 | Wed 4/10/23 | C
3 | Integration with myTNB | Wed 26/7/23 | Mon 7/8/23 |  |  | 33%
| myTNB User Authentication - Source from myTNB Portal | Wed 26/7/23 | Fri 28/7/23 | Wed 26/7/23 | Fri 18/8/23 | C
| myTNB MVSC Application Multiple Entrypoints - Source from myTNB Portal | Mon 31/7/23 | Wed 2/8/23 | Mon 31/7/23 |  | Pending on myTNB
| myTNB MVSC Application Multi-User-Access - Source from myTNB Portal | Thu 3/8/23 | Mon 7/8/23 | Thu 3/8/23 |  | Pending on myTNB
4 | Maintain Old Application | Tue 8/8/23 | Thu 10/8/23
| myTNB Old Application - Maintain old existing Application to be accessible | Tue 8/8/23 | Thu 10/8/23
5 | Application Number | Fri 11/8/23 | Tue 15/8/23 |  |  | 60%
| Application - Application Number - Source from myTNB Portal | Fri 11/8/23 | Tue 15/8/23 |  |  | 60%
6 | Application Status | Wed 16/8/23 | Fri 18/8/23 |  |  | 50%
| Application - Status - Capture Updates - by Employee - Source from ICPP | Wed 16/8/23 | Fri 18/8/23 | Mon 31/7/23 |  | 50%
7 | Application Stages Timeline | Mon 21/8/23 | Thu 31/8/23 |  |  | 82%
| Application - Stages Timeline - Source from EnergySense | Mon 21/8/23 | Wed 23/8/23 | Mon 21/8/23 |  | 80%
| Application - Stages Timeline - Progress/Percentage Fraction Indicators - Source from EnergySense | Thu 24/8/23 | Mon 28/8/23 | Mon 31/7/23 |  | 85%
| Application - Stages Timeline - Free Navigation Between the 3 Stages (Technical Documents Submission, Technical Review & Connection Charges) - Source from EnergySense | Tue 29/8/23 | Thu 31/8/23 | Thu 24/8/23 |  | 80%
8 | Getting Electricity (GE) Eligibility | Fri 1/9/23 | Fri 8/9/23 |  |  | 60%
| myTNB Getting Electricity (GE) Eligibility - by Customer - Source from myTNB Portal | Fri 1/9/23 | Tue 5/9/23 | Fri 8/9/23 |  | 60%
| EnergySense Getting Electricity (GE) Eligibility - by Customer - Source from myTNB Portal | Wed 6/9/23 | Fri 8/9/23 | Fri 8/9/23 |  | 60%
9 | Customer Details | Mon 11/9/23 | Wed 13/9/23
| myTNB Customer Detail - by Customer - Source from myTNB Portal | Mon 11/9/23 | Wed 13/9/23 |  |  | Pending on myTNB
10 | Commercial Documents | Thu 14/9/23 | Mon 18/9/23
| myTNB Commercial Documents - by Customer - Source from myTNB Portal | Thu 14/9/23 | Mon 18/9/23 |  |  | Pending on myTNB
11 | Draft Application | Tue 19/9/23 | Thu 21/9/23
| myTNB Draft Application - by Customer - Source from myTNB Portal | Tue 19/9/23 | Thu 21/9/23 |  |  | Pending on myTNB
12 | Application Submission (non-draft) | Fri 22/9/23 | Fri 29/9/23 |  |  | 30%
| myTNB Application Submission (non-draft) - by Customer - Source from myTNB Portal | Fri 22/9/23 | Tue 26/9/23 |  |  | 60%
| EnergySense Application Submission (non-draft) - by Customer - Source from myTNB Portal | Wed 27/9/23 | Fri 29/9/23 |  |  | 0%
13 | BCRM SR Number | Mon 2/10/23 | Mon 9/10/23 |  |  | 30%
| Application - BCRM SR Number - Source from BCRM via myTNB Portal | Mon 2/10/23 | Wed 4/10/23 |  |  | 60%
| Application - BCRM SR Status Updates - Source from EnergySense via myTNB Portal | Thu 5/10/23 | Mon 9/10/23
14 | ICPP Work Order Number | Wed 26/7/23 | Fri 28/7/23 |  |  | 70%
| Application - Work Order Number - by Employee - Source from ICPP | Wed 26/7/23 | Fri 28/7/23 |  |  | 70%
15 | Basic Information | Mon 31/7/23 | Wed 2/8/23 |  |  | 80%
| Application - Basic Information - Source from EnergySense | Mon 31/7/23 | Wed 2/8/23 | Mon 31/7/23 |  | 80%
16 | Notification Email Recipient | Thu 3/8/23 | Mon 7/8/23 |  |  | C
| Application - Email Recipient - by Customer - Source from myTNB Portal | Thu 3/8/23 | Mon 7/8/23 | Fri 8/9/23 | Fri 22/9/23 | C
17 | Technical Document - Normal Documents | Wed 26/7/23 | Tue 15/8/23 |  |  | 72%
| Technical Document - Normal Documents by Customer - Source from myTNB Portal | Wed 26/7/23 | Fri 28/7/23 | Thu 3/8/23 |  | 60%
| Technical Document – Hold “Normal” Documents for ICPP when no SR number - Source from myTNB Portal | Mon 31/7/23 | Wed 2/8/23 | Wed 26/7/23 |  | 60%
| EnergySense User Interface - Download Normal Document's Attachments data (multiple Attachments) for Employee | Thu 3/8/23 | Mon 7/8/23 | Thu 3/8/23 |  | 40%
| Email Trigger - Upon Normal Document submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Tue 8/8/23 | Thu 10/8/23 | Wed 26/7/23 | Wed 9/8/23 | C
| Technical Document - Master Data of 26 types of Technical Document - Source from EnergySense | Fri 11/8/23 | Tue 15/8/23 | Fri 11/8/23 | Fri 22/9/23 | C
18 | Technical Document - Other Documents | Wed 16/8/23 | Thu 31/8/23 |  |  | 35%
| myTNB Portal User Interface - Add a new non-standard Other Document and set the document name in Technical Documents List | Wed 16/8/23 | Fri 18/8/23 |  |  | 0%
| myTNB Portal User Interface - Edit the name of a previously added Other Document in Technical Documents List | Mon 21/8/23 | Wed 23/8/23 |  |  | 0%
| Technical Document – Hold “Other” Documents for ICPP when no SR number - Source from myTNB Portal | Thu 24/8/23 | Mon 28/8/23 | Wed 26/7/23 |  | 55%
| Email Trigger - Upon Other Document submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Tue 29/8/23 | Thu 31/8/23 | Wed 26/7/23 |  | 85%
19 | Technical Document - Map A Digital Form | Fri 1/9/23 | Tue 26/9/23 |  |  | 28%
| Technical Document - Map A Digital Form for Customer (6 sections, 70 fields) - Source from myTNB Portal | Fri 1/9/23 | Tue 5/9/23 | Fri 1/9/23 |  | 50%
| Technical Document - Map A Digital Form - 11 types of Master Data and Selection Fields - Source from EnergySense | Wed 6/9/23 | Fri 8/9/23 | Wed 26/7/23 |  | 50%
| Technical Document - Map A Submission (6 sections, 70 fields) by Customer - Source from myTNB Portal | Mon 11/9/23 | Wed 13/9/23 |  |  | 0%
| Technical Document – Hold Digital Map A for ICPP when no SR number - Source from myTNB Portal | Thu 14/9/23 | Mon 18/9/23 | Wed 26/7/23 |  | 30%
| Technical Document - Generate Map A PDF (6 sections, 70 fields) - Source from EnergySense | Tue 19/9/23 | Thu 21/9/23 |  |  | 0%
| Email Trigger - Upon Digital Map A submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Fri 22/9/23 | Tue 26/9/23 | Wed 26/7/23 |  | 35%
20 | Technical Document - Others | Wed 27/9/23 | Thu 12/10/23 |  |  | 65%
| Technical Document - Direct Deletion (before Review Initiated) by Customer - Source from myTNB Portal | Wed 27/9/23 | Fri 29/9/23 | Wed 27/9/23 |  | 70%
| Technical Document - Review Initiated by Employee - Source from ICPP | Mon 2/10/23 | Wed 4/10/23 |  |  | 0%
| Technical Document - Submit for Review / Acknowledgement (for whole submission) - by Customer - Source from myTNB Portal | Thu 5/10/23 | Mon 9/10/23 | Wed 27/9/23 |  | 90%
| Email Trigger - Upon Submit for Review / Acknowledgement submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Tue 10/10/23 | Thu 12/10/23 | Tue 3/10/23 | Tue 10/10/23 | C
21 | Technical Review | Tue 8/8/23 | Wed 23/8/23 |  |  | 41%
| Technical Review - Response (for each Technical Document) - main data by Employee - Source from ICPP | Tue 8/8/23 | Thu 10/8/23 | Fri 11/8/23 |  | 95%
| Email Trigger - Upon Technical Document Approved, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Fri 11/8/23 | Tue 15/8/23 | Tue 8/8/23 |  | 65%
| Email Trigger - Upon Technical Document Rejected, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Wed 16/8/23 | Fri 18/8/23 | Tue 8/8/23 |  | 60%
| Technical Review - Response (for each Technical Document) - Multiple Attachments by Employee - Source from ICPP | Mon 21/8/23 | Wed 23/8/23 | Fri 11/8/23 |  | 95%
22 | Ulasan Teknikal | Thu 24/8/23 | Thu 31/8/23 |  |  | 60%
| Ulasan Teknikal (of overall submission) with multiple Attachments by Employee - Source from ICPP | Thu 24/8/23 | Mon 28/8/23 | Wed 26/7/23 |  | 60%
| Ulasan Teknikal - History - Source from EnergySense | Tue 29/8/23 | Thu 31/8/23 | Wed 26/7/23 |  | 60%
23 | Getting Electricity (GE) Qualification | Fri 1/9/23 | Tue 5/9/23 |  |  | 20%
| Application - Getting Electricity (GE) Qualification - by Employee - Source from ICPP | Fri 1/9/23 | Tue 5/9/23 | Fri 1/9/23 |  | 20%
24 | Update Business Area | Wed 6/9/23 | Wed 13/9/23 |  |  | 10%
| myTNB Portal Business Rules - Business Area can no longer be updated by Customer once confirmed in ICPP | Wed 6/9/23 | Fri 8/9/23 |  |  | 0%
| Application - Update Business Area - by Employee - Source from ICPP | Mon 11/9/23 | Wed 13/9/23 | Mon 11/9/23 |  | 20%
25 | Submit Site Progress | Wed 26/7/23 | Mon 7/8/23 |  |  | 63%
| Site Progress - with multiple Attachments by Customer - Source from myTNB Portal | Wed 26/7/23 | Fri 28/7/23 | Wed 26/7/23 | Wed 9/8/23 | C
| EnergySense Backend API - Send Site Progress's Attachments data (multiple Attachments) data to ICPP Backend via SOA | Mon 31/7/23 | Wed 2/8/23 | Mon 18/9/23 |  | 80%
| Email Trigger - Upon Site Progress Submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Thu 3/8/23 | Mon 7/8/23 | Tue 12/9/23 |  | 10%
26 | Supply Required Date | Tue 8/8/23 | Tue 5/9/23 |  |  | 51%
| Update Supply Required Date - with multiple Attachments by Customer - Source from myTNB Portal | Tue 8/8/23 | Thu 10/8/23 | Tue 12/9/23 | Mon 9/10/23 | C
| Backend API - EnergySense send Update Supply Required Date main data to ICPP Backend via SOA | Fri 11/8/23 | Tue 15/8/23 | Tue 12/9/23 |  | 80%
| Email Trigger - Upon Update Supply Required Date request submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Wed 16/8/23 | Fri 18/8/23 |  |  | Pending on ICPP
| Update Supply Required Date - Approval with multiple Attachments (Approve/Reject) by Employee - Source from ICPP | Mon 21/8/23 | Wed 23/8/23 | Fri 1/9/23 |  | 80%
| Email Trigger - Upon Update Supply Required Date Approved, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Thu 24/8/23 | Mon 28/8/23 |  |  | Pending on ICPP
| Email Trigger - Upon Update Supply Required Date Rejected, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Tue 29/8/23 | Thu 31/8/23 |  |  | Pending on ICPP
| Update Supply Required Date - History - Source from EnergySense | Fri 1/9/23 | Tue 5/9/23 | Tue 12/9/23 | Mon 9/10/23 | C
27 | Appointment | Wed 6/9/23 | Fri 20/10/23 |  |  | 43%
| Appointment - by Customer - Source from myTNB Portal | Wed 6/9/23 | Fri 8/9/23 | Mon 18/9/23 | Fri 29/9/23 | C
| EnergySense Backend API - Send Appointment main data to ICPP Backend via SOA | Mon 11/9/23 | Wed 13/9/23 | Mon 11/9/23 |  | 80%
| Email Trigger - Upon Appointment request submitted, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Thu 14/9/23 | Mon 18/9/23 |  |  | Pending on ICPP
| Appointment - Approval (Approve/Reject) by Employee - Source from ICPP | Tue 19/9/23 | Thu 21/9/23 | Mon 18/9/23 |  | 50%
| Email Trigger - Upon Appointment Approved, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Fri 22/9/23 | Tue 26/9/23 |  |  | Pending on ICPP
| Email Trigger - Upon Appointment Rejected, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Wed 27/9/23 | Fri 29/9/23 |  |  | Pending on ICPP
| Appointment - Cancel by Customer - Source from myTNB Portal | Mon 2/10/23 | Wed 4/10/23 | Mon 18/9/23 | Mon 9/10/23 | C
| Email Trigger - Upon Appointment Cancelled by Customer, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Thu 5/10/23 | Mon 9/10/23 |  |  | Pending on ICPP
| Appointment - Cancel by Employee - Source from ICPP | Tue 10/10/23 | Thu 12/10/23 | Mon 18/9/23 |  | 50%
| Email Trigger - Upon Appointment Cancelled by Employee, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Fri 13/10/23 | Tue 17/10/23 |  |  | Pending on ICPP
| Appointment - Reschedule by Customer - Source from myTNB Portal | Wed 18/10/23 | Fri 20/10/23 | Tue 12/9/23 | Mon 9/10/23 | C
28 | Connection Charges | Thu 14/9/23 | Thu 12/10/23 |  |  | 47%
| Connection Charges - Capture Status Update - by Employee - Source from ICPP | Thu 14/9/23 | Mon 18/9/23 | Thu 14/9/23 |  | 80%
| Connection Charges - Required stage - by Employee - Source from ICPP | Tue 19/9/23 | Thu 21/9/23 | Tue 19/9/23 |  | 50%
| Connection Charges – Payment Gateway for Connection Charges | Fri 22/9/23 | Tue 26/9/23 | Fri 22/9/23 |  | 50%
| myTNB Portal Business Rules - Even when Connection Charges Required stage, allow to resubmit technical documents | Wed 27/9/23 | Fri 29/9/23 | Wed 27/9/23 |  | 50%
| Email Trigger - Upon Connection Charges Required by Employee, EnergySense backend trigger ICPP Backend via SOA to send email to Customer/Employee | Mon 2/10/23 | Wed 4/10/23 |  |  | Pending on ICPP
| Connection Charges - Paid stage - by Employee - Source from ICPP | Thu 5/10/23 | Mon 9/10/23 | Wed 27/9/23 |  | 50%
| myTNB Portal Business Rules - Even when Connection Charges Paid stage, allow to resubmit technical documents | Tue 10/10/23 | Thu 12/10/23 | Wed 27/9/23 |  | 50%
29 | Technically Complete | Wed 26/7/23 | Wed 2/8/23
| Application - Technically Complete by Employee - Source from ICPP | Wed 26/7/23 | Fri 28/7/23 |  |  | 0%
| Application - Technically Complete - Carry Over to as-is myTNB's My Project Status - Source from EnergySense | Mon 31/7/23 | Wed 2/8/23 |  |  | 0%
30 | myTNB Dynatrace integration | Thu 3/8/23 | Tue 15/8/23
| myTNB Portal Backend - Trigger to Dynatrace for each outgoing API calls to EnergySense API | Thu 3/8/23 | Mon 7/8/23 |  |  | 0%
| myTNB Portal Backend - Trigger to Dynatrace for each incoming API calls from EnergySense API | Tue 8/8/23 | Thu 10/8/23 |  |  | 0%
| myTNB Portal Business Rules - Monitoring of API requests in Dynatrace | Fri 11/8/23 | Tue 15/8/23 |  |  | 0%
31 | EnergySense | Wed 16/8/23 | Tue 5/9/23 |  |  | 79%
| EnergySense - User Access (via TNB ActiveDirectory) | Wed 16/8/23 | Fri 18/8/23 | Fri 8/9/23 | Mon 9/10/23 | C
| EnergySense - Role Management | Mon 21/8/23 | Wed 23/8/23 | Fri 8/9/23 | Mon 9/10/23 | C
| EnergySense - Statistics Dashboard (Total/Draft/In-progress/Completed) | Thu 24/8/23 | Mon 28/8/23 | Fri 8/9/23 | Mon 9/10/23 | C
| EnergySense - Application table - Comprehensive Filtering Features | Tue 29/8/23 | Thu 31/8/23 | Tue 8/8/23 |  | 50%
| EnergySense - Application table - Export/Download to CSV | Fri 1/9/23 | Tue 5/9/23 | Tue 8/8/23 |  | 45%
32 | Overall | Wed 6/9/23 | Thu 12/10/23
| MVSC Project Management for CR Features | Wed 6/9/23 | Fri 8/9/23
| MVSC End-to-end Testing for CR Features between BCRM, myTNB Portal, EnergySense & ICPP | Mon 11/9/23 | Wed 13/9/23
| EnergySense Pilot Release - Sync with ICPP's Availability and myTNB Portal's Feature Toggle | Thu 14/9/23 | Mon 18/9/23
| EnergySense Pilot Release - Disallow Business Area where ICPP is not available (with myTNB Portal's Feature Toggle) | Tue 19/9/23 | Thu 21/9/23
| myTNB Portal Pilot Release - Feature Toggle - By Business Area & Login ID | Fri 22/9/23 | Tue 26/9/23
| myTNB Portal MVSC Downtime Handler | Wed 27/9/23 | Fri 29/9/23
| myTNB Portal Store XML log into outbound table | Mon 2/10/23 | Wed 4/10/23
| EnergySense Users Training and User Manuals for CR Features | Thu 5/10/23 | Mon 9/10/23
|  | Tue 10/10/23 | Thu 12/10/23
myTNB Portal User Interface - Copywriting for CR Features (English only)
33 | Usability Testing for myTNB Portal | Mon 23/10/23 | Mon 23/10/23 | Tue 8/8/23 |  | 80%
34 | Final System Integration Test (SIT) | Mon 2/10/23 | Tue 10/10/23
| Perform SIT | Mon 2/10/23 | Wed 4/10/23
| Remediation & Redo Testing (Failed Session) | Thu 5/10/23 | Mon 9/10/23
| Final SIT & Sign-off | Tue 10/10/23 | Tue 10/10/23
35 | Final User Acceptance Test (UAT) | Wed 11/10/23 | Thu 19/10/23
| Perform UAT | Wed 11/10/23 | Fri 13/10/23
| Remediation & Redo Testing (Failed Session) | Mon 16/10/23 | Wed 18/10/23
| Final UAT & Sign-off | Thu 19/10/23 | Thu 19/10/23
36 | Deployment to Production Environment & Go Live | Fri 20/10/23 | Fri 27/10/23
| Configure & deploy Production server (MVSC, iCPP and SOA) | Fri 20/10/23 | Tue 24/10/23
| Configure & deploy Production server (myTNB Portal) | Wed 25/10/23 | Fri 27/10/23

## Timeline 18 April 2024
Medium Voltage Supply Connection - MVSC Project Timeline |  |  | Target Start Date | Target Comp. Date | Actual Start Date | Actual End Date | STATUS
No | Activities
1 | User Requirement Specification (URS) & Joint Application Design (JAD) Session |  | Tue 25/2/23 | Mon 3/3/23
| User Requirement Specification (URS) |  | Tue 25/2/23 | Wed 26/2/23 | Tue 25/2/23 | Wed 26/2/23 | C
| - EnergySense MVSC Core functions |  | Thu 27/2/23 | Fri 28/3/23 | Thu 27/2/23 | Fri 28/3/23 | C
| SOA (MVSC-ICPP) interfaces |  | Mon 3/3/23 | Mon 3/3/23 | Mon 3/3/23 | Mon 3/3/23 | C
2 | System Design Session |  | Tue 4/3/23 | Fri 7/3/23
| - System Design for Database |  | Tue 4/3/23 | Thu 5/3/23 | Tue 4/3/23 | Thu 5/3/23 | C
| - System Design for User Interface |  | Wed 5/3/23 | Thu 6/3/23 | Wed 5/3/23 | Thu 6/3/23 | C
| - System Design for Functional Workflow |  | Thu 6/3/23 | Fri 7/3/23 | Thu 6/3/23 | Fri 7/3/23 | C
| User Requirement Sign-off |  | Fri 7/3/23 | Fri 7/3/23 | Fri 7/3/23 | Wed 4/10/23 | C
3 | Integration with myTNB |  | Wed 26/7/23 | Mon 7/8/23 |  |  | C
| myTNB User Authentication - Source from myTNB Portal |  | Wed 26/7/23 | Fri 28/7/23 | Wed 26/7/23 | Fri 18/8/23 | C
4 | Maintain Old Application |  | Tue 8/8/23 | Thu 10/8/23 |  |  | Pending myTNB
| myTNB Old Application - Maintain old existing Application to be accessible |  | Tue 8/8/23 | Thu 10/8/23 |  |  | Pending myTNB
5 | Application Number |  | Fri 11/8/23 | Tue 15/8/23 |  |  | 90%
| Application - Application Number - Source from myTNB Portal |  | Fri 11/8/23 | Tue 15/8/23 |  |  | 90%
6 | Application Status |  | Wed 16/8/23 | Fri 18/8/23 |  |  | 90%
| Application - Status - Capture Updates - by Employee - Source from ICPP |  | Wed 16/8/23 | Fri 18/8/23 | Mon 31/7/23 |  | 90%
7 | Application Stages Timeline |  | Mon 21/8/23 | Thu 31/8/23 |  |  | 90%
| Application - Stages Timeline - Source from EnergySense |  | Mon 21/8/23 | Wed 23/8/23 | Mon 21/8/23 |  | 90%
| Application - Stages Timeline - Progress/Percentage Fraction Indicators - Source from EnergySense |  | Thu 24/8/23 | Mon 28/8/23 | Mon 31/7/23 |  | 90%
| Application - Stages Timeline - Free Navigation Between the 3 Stages (Technical Documents Submission, Technical Review & Connection Charges) - Source from EnergySense |  | Tue 29/8/23 | Thu 31/8/23 | Thu 24/8/23 |  | 90%
8 | Getting Electricity (GE) Eligibility |  | Fri 1/9/23 | Fri 8/9/23 |  |  | 90%
| myTNB Getting Electricity (GE) Eligibility - by Customer - Source from myTNB Portal |  | Fri 1/9/23 | Tue 5/9/23 |  |  | 90%
| EnergySense Getting Electricity (GE) Eligibility - by Customer - Source from myTNB Portal |  | Wed 6/9/23 | Fri 8/9/23 |  |  | 90%
9 | Application Submission (non-draft) |  | Fri 22/9/23 | Fri 29/9/23 |  |  | 90%
| myTNB Application Submission (non-draft) - by Customer - Source from myTNB Portal |  | Fri 22/9/23 | Tue 26/9/23 |  |  | 90%
| EnergySense Application Submission (non-draft) - by Customer - Source from myTNB Portal |  | Wed 27/9/23 | Fri 29/9/23 |  |  | 90%
10 | BCRM SR Number |  | Mon 2/10/23 | Mon 9/10/23 |  |  | 90%
| Application - BCRM SR Number - Source from BCRM via myTNB Portal |  | Mon 2/10/23 | Wed 4/10/23 |  |  | 50%
| Application - BCRM SR Status Updates - Source from EnergySense via myTNB Portal |  | Thu 5/10/23 | Mon 9/10/23 |  |  | 90%
11 | ICPP Work Order Number |  | Wed 26/7/23 | Fri 28/7/23 |  |  | C
| Application - Work Order Number - by Employee - Source from ICPP |  | Wed 26/7/23 | Fri 28/7/23 |  |  | C
12 | Basic Information |  | Mon 31/7/23 | Wed 2/8/23 |  |  | C
| Application - Basic Information - Source from EnergySense |  | Mon 31/7/23 | Wed 2/8/23 | Mon 31/7/23 |  | C
13 | Notification Email Recipient |  | Thu 3/8/23 | Mon 7/8/23 |  |  | C
| Application - Email Recipient - by Customer - Source from myTNB Portal |  | Thu 3/8/23 | Mon 7/8/23 | Fri 8/9/23 | Fri 22/9/23 | C
14 | Technical Document - Normal Documents |  | Wed 26/7/23 | Tue 15/8/23 |  |  | 93%
| Technical Document - Normal Documents by Customer - Source from myTNB Portal |  | Wed 26/7/23 | Fri 28/7/23 |  |  | 90%
| Technical Document – Hold “Normal” Documents for ICPP when no SR number - Source from myTNB Portal |  | Mon 31/7/23 | Wed 2/8/23 | Wed 26/7/23 |  | 90%
| EnergySense User Interface - Download Normal Document's Attachments data (multiple Attachments) for Employee |  | Thu 3/8/23 | Mon 7/8/23 |  |  | 90%
| Technical Document - Master Data of 26 types of Technical Document - Source from EnergySense |  | Fri 11/8/23 | Tue 15/8/23 | Fri 11/8/23 | Fri 22/9/23 | C
15 | Technical Document - Other Documents |  | Wed 16/8/23 | Thu 31/8/23 |  |  | 90%
| myTNB Portal User Interface - Add a new non-standard Other Document and set the document name in Technical Documents List |  | Wed 16/8/23 | Fri 18/8/23 |  |  | 90%
| myTNB Portal User Interface - Edit the name of a previously added Other Document in Technical Documents List |  | Mon 21/8/23 | Wed 23/8/23 |  |  | 90%
| Technical Document – Hold “Other” Documents for ICPP when no SR number - Source from myTNB Portal |  | Thu 24/8/23 | Mon 28/8/23 | Wed 26/7/23 |  | 90%
16 | Technical Document - Map A Digital Form |  | Fri 1/9/23 | Tue 26/9/23 |  |  | 92%
| Technical Document - Map A Digital Form for Customer (6 sections, 70 fields) - Source from myTNB Portal |  | Fri 1/9/23 | Tue 5/9/23 |  |  | C
| Technical Document - Map A Digital Form - 11 types of Master Data and Selection Fields - Source from EnergySense |  | Wed 6/9/23 | Fri 8/9/23 | Wed 26/7/23 |  | 90%
| Technical Document - Map A Submission (6 sections, 70 fields) by Customer - Source from myTNB Portal |  | Mon 11/9/23 | Wed 13/9/23 |  |  | 90%
| Technical Document – Hold Digital Map A for ICPP when no SR number - Source from myTNB Portal |  | Thu 14/9/23 | Mon 18/9/23 | Wed 26/7/23 |  | 90%
| Technical Document - Generate Map A PDF (6 sections, 70 fields) - Source from EnergySense |  | Tue 19/9/23 | Thu 21/9/23 |  |  | 90%
17 | Technical Document - Others |  | Wed 27/9/23 | Thu 12/10/23 |  |  | 90%
| Technical Document - Direct Deletion (before Review Initiated) by Customer - Source from myTNB Portal |  | Wed 27/9/23 | Fri 29/9/23 |  |  | 90%
| Technical Document - Review Initiated by Employee - Source from ICPP |  | Mon 2/10/23 | Wed 4/10/23 |  |  | 90%
| Technical Document - Submit for Review / Acknowledgement (for whole submission) - by Customer - Source from myTNB Portal |  | Thu 5/10/23 | Mon 9/10/23 |  |  | 90%
18 | Technical Review |  | Tue 8/8/23 | Wed 23/8/23 |  |  | C
| Technical Review - Response (for each Technical Document) - main data by Employee - Source from ICPP |  | Tue 8/8/23 | Thu 10/8/23 |  |  | C
| Technical Review - Response (for each Technical Document) - Multiple Attachments by Employee - Source from ICPP |  | Mon 21/8/23 | Wed 23/8/23 |  |  | C
19 | Ulasan Teknikal |  | Thu 24/8/23 | Thu 31/8/23 |  |  | 95%
| Ulasan Teknikal (of overall submission) with multiple Attachments by Employee - Source from ICPP |  | Thu 24/8/23 | Mon 28/8/23 | Wed 26/7/23 |  | C
| Ulasan Teknikal - History - Source from EnergySense |  | Tue 29/8/23 | Thu 31/8/23 | Wed 26/7/23 |  | 90%
20 | Getting Electricity (GE) Qualification |  | Fri 1/9/23 | Tue 5/9/23 |  |  | 90%
| Application - Getting Electricity (GE) Qualification - by Employee - Source from ICPP |  | Fri 1/9/23 | Tue 5/9/23 |  |  | 90%
21 | Update Business Area |  | Wed 6/9/23 | Wed 13/9/23 |  |  | 90%
| myTNB Portal Business Rules - Business Area can no longer be updated by Customer once confirmed in ICPP |  | Wed 6/9/23 | Fri 8/9/23 |  |  | 90%
| Application - Update Business Area - by Employee - Source from ICPP |  | Mon 11/9/23 | Wed 13/9/23 |  |  | 90%
22 | Submit Site Progress |  | Wed 26/7/23 | Mon 7/8/23 |  |  | C
| Site Progress - with multiple Attachments by Customer - Source from myTNB Portal |  | Wed 26/7/23 | Fri 28/7/23 | Wed 26/7/23 | Wed 9/8/23 | C
| EnergySense Backend API - Send Site Progress's Attachments data (multiple Attachments) data to ICPP Backend via SOA |  | Mon 31/7/23 | Wed 2/8/23 | Mon 18/9/23 |  | C
23 | Supply Required Date |  | Tue 8/8/23 | Tue 5/9/23 |  |  | C
| Update Supply Required Date - with multiple Attachments by Customer - Source from myTNB Portal |  | Tue 8/8/23 | Thu 10/8/23 | Tue 12/9/23 | Mon 9/10/23 | C
| Backend API - EnergySense send Update Supply Required Date main data to ICPP Backend via SOA |  | Fri 11/8/23 | Tue 15/8/23 |  |  | C
| Update Supply Required Date - Approval with multiple Attachments (Approve/Reject) by Employee - Source from ICPP |  | Mon 21/8/23 | Wed 23/8/23 |  |  | C
| Update Supply Required Date - History - Source from EnergySense |  | Fri 1/9/23 | Tue 5/9/23 | Tue 12/9/23 | Mon 9/10/23 | C
24 | Appointment |  | Wed 6/9/23 | Fri 20/10/23 |  |  | 95%
| Appointment - by Customer - Source from myTNB Portal |  | Wed 6/9/23 | Fri 8/9/23 | Mon 18/9/23 | Fri 29/9/23 | C
| EnergySense Backend API - Send Appointment main data to ICPP Backend via SOA |  | Mon 11/9/23 | Wed 13/9/23 |  |  | C
| Appointment - Approval (Approve/Reject) by Employee - Source from ICPP |  | Tue 19/9/23 | Thu 21/9/23 | Mon 18/9/23 |  | C
| Appointment - Cancel by Customer - Source from myTNB Portal |  | Mon 2/10/23 | Wed 4/10/23 | Mon 18/9/23 | Mon 9/10/23 | C
| Appointment - Cancel by Employee - Source from ICPP |  | Tue 10/10/23 | Thu 12/10/23 | Mon 18/9/23 |  | 90%
| Appointment - Reschedule by Customer - Source from myTNB Portal |  | Wed 18/10/23 | Fri 20/10/23 | Tue 12/9/23 | Mon 9/10/23 | C
25 | Connection Charges |  | Thu 14/9/23 | Thu 12/10/23 |  |  | 90%
| Connection Charges - Capture Status Update - by Employee - Source from ICPP |  | Thu 14/9/23 | Mon 18/9/23 |  |  | 90%
| Connection Charges - Required stage - by Employee - Source from ICPP |  | Tue 19/9/23 | Thu 21/9/23 |  |  | 90%
| Connection Charges – Payment Gateway for Connection Charges |  | Fri 22/9/23 | Tue 26/9/23 |  |  | 90%
| myTNB Portal Business Rules - Even when Connection Charges Required stage, allow to resubmit technical documents |  | Wed 27/9/23 | Fri 29/9/23 |  |  | 90%
| Connection Charges - Paid stage - by Employee - Source from ICPP |  | Thu 5/10/23 | Mon 9/10/23 |  |  | 90%
| myTNB Portal Business Rules - Even when Connection Charges Paid stage, allow to resubmit technical documents |  | Tue 10/10/23 | Thu 12/10/23 |  |  | 90%
26 | Technically Complete |  | Wed 26/7/23 | Wed 2/8/23
| Application - Technically Complete by Employee - Source from ICPP |  | Wed 26/7/23 | Fri 28/7/23 |  |  | Pending ICPP
| Application - Technically Complete - Carry Over to as-is myTNB's My Project Status - Source from EnergySense |  | Mon 31/7/23 | Wed 2/8/23 |  |  | Pending myTNB
27 | myTNB Dynatrace integration |  | Thu 3/8/23 | Tue 15/8/23
| myTNB Portal Backend - Trigger to Dynatrace for each outgoing API calls to EnergySense API |  | Thu 3/8/23 | Mon 7/8/23 |  |  | Pending myTNB
| myTNB Portal Backend - Trigger to Dynatrace for each incoming API calls from EnergySense API |  | Tue 8/8/23 | Thu 10/8/23 |  |  | Pending myTNB
| myTNB Portal Business Rules - Monitoring of API requests in Dynatrace |  | Fri 11/8/23 | Tue 15/8/23 |  |  | Pending myTNB
28 | EnergySense |  | Wed 16/8/23 | Tue 5/9/23 |  |  | C
| EnergySense - User Access (via TNB ActiveDirectory) |  | Wed 16/8/23 | Fri 18/8/23 | Fri 8/9/23 | Mon 9/10/23 | C
| EnergySense - Role Management |  | Mon 21/8/23 | Wed 23/8/23 | Fri 8/9/23 | Mon 9/10/23 | C
| EnergySense - Statistics Dashboard (Total/Draft/In-progress/Completed) |  | Thu 24/8/23 | Mon 28/8/23 | Fri 8/9/23 | Mon 9/10/23 | C
| EnergySense - Application table - Comprehensive Filtering Features |  | Tue 29/8/23 | Thu 31/8/23 | Tue 8/8/23 |  | C
| EnergySense - Application table - Export/Download to CSV |  | Fri 1/9/23 | Tue 5/9/23 | Tue 8/8/23 |  | C
29 | Overall |  | Wed 6/9/23 | Thu 12/10/23
| MVSC End-to-end Testing for CR Features between BCRM, myTNB Portal, EnergySense & ICPP |  | Mon 11/9/23 | Wed 13/9/23
| EnergySense Pilot Release - Sync with ICPP's Availability and myTNB Portal's Feature Toggle |  | Thu 14/9/23 | Mon 18/9/23
| EnergySense Pilot Release - Disallow Business Area where ICPP is not available (with myTNB Portal's Feature Toggle) |  | Tue 19/9/23 | Thu 21/9/23
| myTNB Portal Pilot Release - Feature Toggle - By Business Area & Login ID |  | Fri 22/9/23 | Tue 26/9/23
| myTNB Portal MVSC Downtime Handler |  | Wed 27/9/23 | Fri 29/9/23
| myTNB Portal Store XML log into outbound table |  | Mon 2/10/23 | Wed 4/10/23
| EnergySense Users Training and User Manuals for CR Features |  | Thu 5/10/23 | Mon 9/10/23
| myTNB Portal User Interface - Copywriting for CR Features (English only) |  | Tue 10/10/23 | Thu 12/10/23
30 | Usability Testing for myTNB Portal |  | Mon 23/10/23 | Mon 23/10/23 | Tue 8/8/23 |  | 80%
31 | Code merge between MVSC and myTNB. |  | Fri 03/11/23 | Thu 09/11/23 |  |  | C
32 | System Integration Test (SIT) MVSC with ICPP |  | Fri 10/5/2024 | Fri 10/5/2024
Perform 1st Pre- SIT
Remediation & Redo Testing (Failed Session)
| Perform 2nd Pre- SIT | 5 days
SIT & Sign-off
33 | Final System Integration Test (SIT) |  | Fri 24/5/2024 | Fri 24/5/2024
Perform SIT
Remediation & Redo Testing (Failed Session)
Final SIT & Sign-off
34 | Final User Acceptance Test (UAT) |  | Fri 14/6/2024 | Fri 14/6/2024
Perform UAT
Remediation & Redo Testing (Failed Session)
Final UAT & Sign-off
35 | Deployment to Production Environment & Go Live |  | Fri 30/08/24 | Fri 30/08/24
Configure & deploy Production server (MVSC, iCPP and SOA)
Configure & deploy Production server (myTNB Portal)