## Slide 1: MEDIUM VOLTAGE SUPPLY CONNECTION IN ENERGYSENSE (MVSC)
WEEKLY PROJECT STATUS
3rd May 2024

## Slide 2
KEY MILESTONES | PLANNED START | PLANNED END | ACTUAL START | ACTUAL END | STATUS
User Requirement Specification (URS) & Joint Application Design (JAD) Session | 25-Feb-23 | 3-Mar-23 | 25-Feb-22 | 21-Jul-22 | C
User Requirement Sign-Off | 7-Mar-22 | 7-Mar-22 | 7-Mar-22 |  | C
System Design Session | 4-Mar-23 | 7-Mar-23 | 2-Jan-23 | 4-Mar-23 | C
Development |  |  |  |  | 
Integration with myTNB | 26-Aug-23 | 7-Aug-23 |  |  | c
Maintain Old Application | 8-Aug-23 | 10-Aug-23 |  |  | 
Application Number | 11-Aug-23 | 15-Aug-23 |  |  | 90%
Application Status | 16-Aug-23 | 18-Aug-23 | 31-Jul-23 |  | 90%
Application Stages Timeline | 21-Aug-23 | 31-Aug-23 | 31-Jul-23 |  | 90%
Getting Electricity (GE) Eligibility | 1-Sept-23 | 8-Sept-23 |  |  | 90%
Application Submission (non-draft) | 22-Sept-23 | 29-Sept-23 |  |  | 90%
TRAINING & CLOSE
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY
PROJECT PROGRESS | Planned Start
Actual % | Planned %
Chart: 
BUILD
ANALYSE & DESIGN
PLANNING
INITIATION
TRAINING & CLOSE
ACHIEVEMENTS/ KEY HIGHLIGHTS
Functional Design Document Review – Completed with minor comments from En. Ghaffar
Completed on time
On track
On going but might be delayed
Completed but delay
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 3rd May 2024 | CONTRACT PERIOD: | 3 years
ONGOING ACTIVITIES
Application Status Application Stages Timeline Application Number Getting Electricity (GE) Eligibility Application Submission (non-draft) Usability Test Sign-off Code merge between MVSC and myTNB. Bug Fixing
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 14.8 | 85.2
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 2.7 | 97.3
UPCOMING 2 WEEKS ACTIVITIES
To complete and sign off UI/UX design and functional design from Retail by 9th May 2024 To complete SIT test by 10th May 2024 (MVSC – ICPP) To complete and sign off UI/UX design, functional design and usability test from Retail by 17th May 2024 Get updates on myTNB AWS issue from ICT Session with SOA and ICPP to resolve document issues on 6th May 2024 at 11.30 am Session with En. Hafizi on 10th May 2024

## Slide 3
KEY MILESTONES | PLANNED START | PLANNED END | ACTUAL START | ACTUAL END | STATUS
BCRM SR Number | 2-Oct-23 | 9-Oct-23 |  |  | 90%
ICPP Work Order Number | 26-Jul-23 | 28-Jul-23 |  |  | c
Basic Information | 31-Jul-23 | 2-Aug-23 | 31-Jul-23 |  | c
Notification Email Recipient | 3-Aug-23 | 7-Aug-23 | 8-Aug-23 |  | c
Technical Document - Normal Documents | 26-Jul-23 | 15-Aug-23 | 26-July-23 |  | 93%
Technical Document - Other Documents | 16-Aug-23 | 31-Aug-23 | 26-July-23 |  | 90%
Technical Document - Map A Digital Form | 1-Sept-23 | 26-Sept-23 | 26-July-23 |  | 92%
Technical Document – Others | 27-Sept-23 | 12-Oct-23 |  |  | 90%
Technical Review | 8-Aug-23 | 23-Aug-23 | 8-Aug-23 |  | 95%
Ulasan Teknikal | 24-Aug-23 | 31-Aug-23 | 26-July-23 |  | 90%
Getting Electricity (GE) Qualification | 1-Sept-23 | 5-Sept-23 |  |  | 90%
Update Business Area | 6-Sept-23 | 13-Sept-23 |  |  | 90%
Submit Site Progress | 26-Jul-23 | 7-Aug-23 | 26-July-23 |  | c
Supply Required Date | 8-Aug-23 | 5-Sept-23 | 12-Sept-23 |  | c
Appointment | 6-Sept-23 | 20-Oct23 | 21-Sept-23 |  | 95%
Connection Charges | 14-Sept-23 | 12-Oct-23 |  |  | c
TRAINING & CLOSE
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY
PROJECT PROGRESS | Planned Start
Actual % | Planned %
Chart: 
BUILD
ANALYSE & DESIGN
PLANNING
INITIATION
TRAINING & CLOSE
ACHIEVEMENTS/ KEY HIGHLIGHTS
ICPP Work Order Number Basic Information Notification Email Recipient Submit Site Progress Supply Required Date Connection Charges
Completed on time
On track
On going but might be delayed
Completed but delay
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 3rd May 2024 | CONTRACT PERIOD: | 3 years
ONGOING ACTIVITIES
Assigning requirement/task for developer. BCRM SR Number Basic Information Technical Document - Normal Documents Ulasan Teknikal Code merge between MVSC and myTNB. Bug Fixing
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 14.8 | 85.2
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 2.9 | 98.1
UPCOMING 2 WEEKS ACTIVITIES
To complete and sign off UI/UX design and functional design from Retail by 9th May 2024 To complete SIT test by 10th May 2024 (MVSC – ICPP) To complete and sign off UI/UX design, functional design and usability test from Retail by 17th May 2024 Get updates on myTNB AWS issue from ICT Session with SOA and ICPP to resolve document issues on 6th May 2024 at 11.30 am Session with En. Hafizi on 10th May 2024

## Slide 4
KEY MILESTONES | PLANNED START | PLANNED END | ACTUAL START | ACTUAL END | STATUS
Technically Complete | 26-Jul-23 | 2-Aug-23 |  |  | 
myTNB Dynatrace integration | 3-Aug-23 | 15-Aug-23 |  |  | 
EnergySense | 16-Aug-23 | 5-Spt-23 | 8-Aug-23 |  | C
Overall | 6-Sept-23 | 12-Oct-23 |  |  | 
Usability Testing for myTNB Portal | 23-Oct-23 | 16-May-24 | 8-Aug-23 |  | 80%
Code merge between MVSC and myTNB. | 3-Nov-23 | 9-Nov-24 |  |  | C
System Integration Test (SIT) MVSC with ICPP | 25.-Mar-24 | 10-May-24 | 25-Mar-24 |  | 80%
Final System Integration Test (SIT) | 29-Apr-24 | 24-May-24 |  |  | 
Final User Acceptance Test (UAT) | 27-May-24 | 14-June-24 |  |  | 
Deployment to Production Environment & Go Live | 17-June-24 | 31-August-24 |  |  | 
TRAINING & CLOSE
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY
PROJECT PROGRESS | Planned Start
Actual % | Planned %
BUILD
ANALYSE & DESIGN
PLANNING
INITIATION
TRAINING & CLOSE
ACHIEVEMENTS/ KEY HIGHLIGHTS
Energy Sense Code merge between MVSC and myTNB.
Completed on time
On track
On going but might be delayed
Completed but delay6
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 3rd May 2024 | CONTRACT PERIOD: | 3 years
ONGOING ACTIVITIES
Usability Testing for myTNB Portal System Integration Test (SIT) MVSC with ICPP
Chart: 
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 14.8 | 85.2
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 2.9 | 98.1
UPCOMING 2 WEEKS ACTIVITIES
To complete and sign off UI/UX design and functional design from Retail by 9th May 2024 To complete SIT test by 10th May 2024 (MVSC – ICPP) To complete and sign off UI/UX design, functional design and usability test from Retail by 17th May 2024 Get updates on myTNB AWS issue from ICT by 3rd May 2024 Session with SOA and ICPP to resolve document issues on 6th May 2024 at 11.30 am Session with En. Hafizi on 10th May 2024

## Slide 5
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 27th October 2023
PROJECT MANAGER (Innotech): | Tieu Jue Yue | REPORT DATE: | 3rd May 2024 | CONTRACT PERIOD: | 3 years
TOP 3 ISSUES AND RECOMMENDATIONS | PLANNED START |  |  |  | ACTUAL START | 
No. | Issue | Category | Resolution | PIC | Due Date | Status
1 | VPN cannot be accessed | High | Developers to go to TNB premise to continue working on development | Innotech / TNB | - | Open
2 | myTNB AWS Issue (code cannot be built locally) | High | Contacted ICT to identify potential problems (Pending Updates from ICT) | Innotech / TNB | 3rd May 2024 | Open
TOP 3 RISKS AND MITIGATIONS | PLANNED END |  |  |  |  | ACTUAL START |  | 
No. | Risk | Likelihood | Impact | Category | Mitigation | PIC | Due Date | Status
ACTION LIST | PLANNED START |  | ACTUAL START | 
No. | Action | PIC | Due Date | Status
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY

## Slide 6
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 28th July 2023
PROJECT MANAGER (Innotech): | Nashmi Shah Nalkatli | REPORT DATE: | 18th April 2024 | CONTRACT PERIOD: | 3 years
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY

## Slide 7
PAYMENT MILESTONES | PAYMENT MILESTONES |  | 
No. | Milestones Description | % | Status
MVSC IMPLEMENTATION |  |  | 
1. | Kick-Off and URS Sign-Off | 30% | PAID
2. | Sprint 1 UAT Sign Off and Tech Service Go Live | 20% | 
3. | Sprint 2 UAT Sign Off and Tech Service Go Live | 20% | 
4. | Sprint 3 UAT Sign Off and Tech Service Go Live | 20% | 
5. | Technical Documentation and Service Proj Closure | 10% | 
PROJECT MANAGER (TNB): | Nurelahajaraha binti Mahamed Ramly | START DATE: | 24th February 2022 | END DATE: | 28th July 2023
PROJECT MANAGER (Innotech): | Nashmi Shah Nalkatli | REPORT DATE: | 27th July 2023 | CONTRACT PERIOD: | 3 years
Medium Voltage Supply Connection in EnergySense (MVSC)
PROJECT STATUS SUMMARY